## Tabelle1
Date | Hours | Task Description | Done By
2025-11-22 | 2 | Set up project folder and virtual environment, install necessary Python libraries | Nico Weder
2025-11-26 | 6 | Searched, explored and downloaded datasets: electricity production, LCOE, CO₂ emissions | Nico Weder
2025-11-30 | 2 | Further exploration | Nico Weder
2025-11-01 | 3 | Created stacked area chart of global electricity production | Nico Weder
2025-11-03 | 2 | Complete the lineplots for renewable vs fossil and the renewable share | Nico Weder
2025-11-18 | 2 | Added hatching and color coding for renewables and nuclear to stacked area chart, changed order of them | Nico Weder
2025-11-20 | 3 | Explored LCOE dataset, combined similar technologies and discount rates | Nico Weder
2025-11-22 | 3 | Created boxplots for LCOE distribution per technology | Nico Weder
2025-11-25 | 3 | Merged with energy dataset for latest year, calculated relevant metrics | Nico Weder
2025-11-28 | 4 | Created scatter plot of CO₂ per capita vs renewable share with scaled bubble sizes, added highlights for selected countries | Nico Weder
2025-11-30 | 4 | Adjusted chart styling, gridlines, colorbars, labels, and annotations for readability | Nico Weder
2025-12-18 | 3 | Finalized all charts and verified consistency of labels, colors, and datasets | Nico Weder
2025-12-19 | 2 | Generated HTML output from Quarto, checked if everythings correct | Nico Weder
2026-01-04 | 1 | Tested index.html file and code on other PC so it is ready for submission | Nico Weder
2026-01-05 | 4 | Cleaned project folder for submission: removed unnecessary files used for dataexploration and added read me file. | Nico Weder
2026-01-06 | 1 | Planning writing of final report: outlined sections, key points, other things to include | Nico Weder
2026-01-07 | 6 | Writing final report: Introduction, Data Exploration, Motivation, Visualization Choices, Key Insights | Nico Weder
2026-01-08 | 6 | Writing final report: Analysis, Conclusion, Citations, Prepare for submission | Nico Weder